## Cost Estimation & Budget
A (WBS ID) | B (Task Name) | C (Assigned To) | D (Duration Days) | E (Unit Cost PKR/day) | F (Qty = Person-Days) | G (Subtotal PKR = E×F) | H (Notes)
1.1.1 | Project Charter & Stakeholder Analysis | Ahmad Tashfeen | 3 | 2000 | 3 | 6000 | Initiation activity
1.1.2 | High-Level Requirements & Feasibility | Ahmad Tashfeen | 3 | 2000 | 3 | 6000 | Follows charter completion
1.1.3 | Supervisor Review & Approval (M1) | Supervisor | 1 | 1500 | 1 | 1500 | External dependency
1.2.1 | Scope Statement & WBS Development | Ahmad Tariq | 3 | 2000 | 3 | 6000 | After M1 approval
1.2.2 | Schedule, Resource & Risk Planning | Ahmad Tariq | 3 | 2000 | 3 | 6000 | Needs approved scope
1.2.3 | Scope Management Plan | Ahmad Tariq | 2 | 2000 | 2 | 4000 | Can overlap with 1.2.4
1.2.4 | Dataset Acquisition & Cleaning | Ahmad Tariq | 3 | 2000 | 3 | 6000 | Before model training
1.3.1 | Sprint 1 – Model Design & Training | Umer Qureshi | 4 | 2000 | 4 | 8000 | Initial ML prototype
1.3.2 | Integration with Mock Bug Tracker UI | Umer Qureshi | 3 | 2000 | 3 | 6000 | Post model stability
1.3.3 | Review & Adjust (End Sprint 1) | Umer Qureshi | 3 | 2000 | 3 | 6000 | Sprint 1 refinement
1.3.4 | Sprint 2 – Refinement & Additions | Umer Qureshi | 5 | 2000 | 5 | 10000 | Further model tuning
1.3.5 | Sprint 2 – Testing & Feedback | Umer Qureshi | 5 | 2000 | 5 | 10000 | QA and user feedback
1.4.1 | Final Testing & Documentation | All Members | 5 | 2000 | 5 | 10000 | Final integration
1.4.2 | Final Presentation & Lessons Learned | All Members | 5 | 2000 | 5 | 10000 | Before submission
1.4.3 | Supervisor Approval & Submission (M4) | Supervisor | 5 | 1500 | 5 | 7500 | External final review
| Total Direct Cost |  |  |  |  | 103000
| Contingency (10%) |  |  |  |  | 10300
| Total Budget (BAC) |  |  |  |  | 113300

## EVM Assumptions & Inputs
Label | Value | Notes
BAC (Budget at Completion) | 113300 | BAC from Cost Estimation & Budget
Planned % Complete (PV%) | 0.6 | 60% of work was planned to be done by now
Actual % Complete (EV%) | 0.45 | 45% of work is actually completed
Actual Cost (as % of BAC) | 0.52 | 52% of the total budget has been spent
Planned Duration (days) | 53 | Total project duration from WBS
Elapsed Time (months) | 3 | After 3 months of project progress
Team Members | Ahmad Tashfeen, Ahmad Tariq, Umer Qureshi
Project Title | Bug Triage AI Agent

## EVM Calculations
Metric | Value | Notes | Interpretation
BAC (PKR) | 113300 | Pulls Budget at Completion | Total Budget
PV (PKR) | 67980 | Planned Value = BAC × PV% | Planned Value
EV (PKR) | 50985 | Earned Value = BAC × EV% | Earned Value
AC (PKR) | 58916 | Actual Cost = BAC × AC% | Actual Cost
CV (PKR) | -7931 | Cost Variance = EV – AC | Negative -> Over Budget
SV (PKR) | -16995 | Schedule Variance = EV – PV | Negative -> Behind Schedule
CPI | 0.86538 | Cost Performance Index = EV ÷ AC | <1 -> Cost Inefficiency
SPI | 0.75 | Schedule Performance Index = EV ÷ PV | <1 -> Schedule Delay
EAC (PKR) | 130924.4444 | Estimate at Completion = BAC ÷ CPI | Project will cost more
Planned Duration (days) | 53 | Planned project duration from WBS
Planned Duration (months) | 1.7667 | Approx. planned months
Estimated Total Duration (months) | 2.3556 | Adjusted for schedule performance (Planned ÷ SPI) | Project may extend by 8-10 days
Elapsed Months (assumed) | 3 | Time passed (given = 3 months)
Estimated Remaining Months | 0 | Remaining duration = total − elapsed

## EV Chart Data
Month | PV (PKR) | EV (PKR) | AC (PKR) | Notes
0 | 0 | 0 | 0 | Project start
1 | 22660 | 16995 | 19638.6667 | End of Month 1
2 | 45320 | 33990 | 39277.3333 | End of Month 2
3 | 67980 | 50985 | 58916 | End of Month 3 (current)